Project Procurement Policy

## Section A: Purpose

| Introduction | This policy defines the mandatory standards and governance framework for procuring goods, services, materials and plant hire across Velocity Civil’s mid-tier civil design and construction portfolio. |
| --- | --- |
| Purpose | - Ensure all structural and pavement materials comply with engineering designs, Australian Standards and heavy-vehicle load specifications. - Standardise procurement workflows across all active civil project sites. - Prevent site stand-downs through structured vendor management, critical-path buffering and supply chain risk mitigation. - Enforce statutory compliance with Heavy Vehicle National Law (HVNL) Chain of Responsibility (CoR) protocols and local environmental guidelines. |
| Target Audience | Operations Manager, Project Procurement Manager, Project Managers, Procurement Engineers, Site Supervisors, Executive Leadership. |

## Section B: Procurement Thresholds and Financial Governance

| All procurement decisions must adhere to strict financial delegation limits to maintain fiscal responsibility and clear audit trails: |  |  |
| --- | --- | --- |
| Contract / Purchase Order Value (AUD) | Required Sourcing Process | Approval Authority |
| $0 – $10,000 | - Direct purchase from pre-qualified vendor list | - Site Supervisor / Procurement Officer |
| $10,001 – $50,000 | - Minimum 2 written competitive quotes | - Project Manager |
| $50,001 – $250,000 | - Minimum 3 formal written quotes + Evaluation Matrix | - Operations Manager / Project Procurement Manager / Senior Project Manager |
| >$250,000 | - Formal Select/Open Tender + Procurement Management Plan | - General Manager / Executive Board |

### Section C: Supplier Selection and Evaluation Criteria

| Vendors evaluated for primary or secondary supply packages must be assessed using Velocity Civil’s standard selection matrix. |  |
| --- | --- |
| - Technical and structural compliance (30%) ── Certified to AS/NATA/SM1600 standards. - Commercial competitiveness (25%) ── Fixed unit rates, clear freight/demurrage terms. - Lead time and schedule buffer] (20%) ── Ability to commit to staged delivery window. - Supply chain resilience (15%) ── Dual-sourcing capacity & local buffer stocks. - Safety Compliance (10%) ──Heavy transport and site delivery protocols. |  |
| Technical Verification | - Suppliers must provide certified Technical Data Sheets (TDS), design calculations and NATA test certificates prior to contract execution. |
| Dual-Sourcing Requirement | - For critical-path materials procurement plans must identify a pre-qualified secondary regional supplier as an active fallback. |

### Section D: Quality Assurance and Material Verification Gateways

| To prevent non-conforming materials from reaching active construction fronts, the following gatekeeper protocols apply. |  |
| --- | --- |
| Pre-Dispatch Review | Any proposed material brand or class substitutions must be submitted to the Engineering QA/QC team with pre-attached TDS and compliance certificates at least 5 business days prior to dispatch. |
| Site Gate Receiving Inspections | Site Supervisors must log all incoming deliveries, verify dockets against the approved Purchase Order (PO), inspect for transport damage and archive site delivery QA photos. |
| Non-Conformance Reports (NCR) | Unapproved material substitutions, cracked structural units or non-conforming aggregates will be rejected at the site gate under a formal NCR at the supplier's expense. |

## Section E: Delivery Staging and Site Integration

| Schedule Buffering | Mandatory 5 to 10-day buffer windows must be embedded into critical-path schedules for all long-lead structural assets. |
| --- | --- |
| All-Weather Staging Pads | Project sites must establish heavy-duty, all-weather gravel staging pads near the site entrance to enable safe, immediate offloading and batch staging upon arrival. |
| Workfront Flexibility | If a supplier experiences an approved delivery delay, Project Managers are required to re-sequence civil earthworks to non-critical sectors to maintain plant and labour productivity. |

### Section F: Sustainable Procurement and Local Content

| Velocity Civil prioritises economic and environmental sustainability within regional project boundaries. |  |
| --- | --- |
| Local Sourcing Preference | Where technical compliance and commercial terms are equal, regional vendors will be prioritised to reduce transport haulage costs and lower carbon emissions. |
| Recycled & Low-Carbon Materials | Sourcing teams are encouraged to evaluate approved crushed recycled concrete and supplementary cementitious materials where permissible under project engineering specifications. |

### Section G: Enforcement

| Enforcement | Compliance with this policy is mandatory for all Velocity Civil personnel. Non-compliance may result in disciplinary action and revocation of financial delegation authority. |
| --- | --- |

## Section H: Document Control Register

| Document Identifier | VC-POL_PROC_001 |
| --- | --- |
| Current Version | 1.0 |
| Effective Date | 03/08/2026 |
| Review Date | 03/08/2027 |
| Document Owner | Operations Manager and Procurement Manager |
| Status | Approved |
| Version History | 03/08/2026 Approved and released for organisation-wide implementation. |