Project Brief – Link Road Re-Alignment and Upgrade

| Activity Road re-alignment and upgrade | Location Section 3B, Abercrombie Way, Trunkey Creek NSW 2795 |
| --- | --- |

## Section A: Project Brief

Velocity Civil has been awarded a contract by the regional road authority to perform a comprehensive geometric realignment, pavement rehabilitation, and structural upgrade of a 3.2-kilometer corridor of rural roadway to transition the asset into a high-capacity, heavy-vehicle freight route.

## Section B: Project Overview

### Project Deliverables

Full reconstruction, geometric correction and pavement rehabilitation across 3,000 m2 of heavy-vehicle structural road pavement (including associated sub-base drainage and safety barriers).

### Project Objectives

- Timeline: Complete all works within the client’s strict schedule requirements.

- Quality and Specifications: Fully comply with regional civil construction and pavement design specifications.

- Financial: Procure all plant, labour and materials within the defined budget to achieve target project margin.

### Project Duration

Six (6) months

### Contract Value

- Total Contract Price: $400,000

- Cost Objectives:

  - Keep direct project costs below $220,000.

  - Eliminate waste, rework and unapproved plant demurrage.

## Section C: Resource Requirements and Cost Breakdown

The construction contract establishes a baseline material cost of $50 per m2 for structural asphalt/pavement layer installation.

### Material Procurement Requirements and Unit Costs

| Material Item | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- |
| Heavy-duty structural pavement | 3,000 m2 | $50.00 / m2 | $150,000.00 |
| Sub-surface drainage pipe (J-channel equivalent.) | 300 m | $1.57 / m | $471.00 |
| Edge restraint / sub-grade lining (undersill equivalent) | 20 m | $1.97 / m | $39.40 |
| Kerb transition / starter rail (starter strip equivalent) | 20 m | $1.61 / m | $32.20 |
| Total Materials Cost |  |  | $150,542.60 |

### Labour / Human Resource Requirements

| Role | Total Hours | Hourly Rate | Total Cost |
| --- | --- | --- | --- |
| 1 Project Civil Engineer / Project Manager and Project Procurement Manager | 150 hrs | $60.00 / hr | $9,000.00 |
| 3 Experienced Civil Operators / Plant Crew | 600 hrs | $40.00 / hr | $21,000.00 |
| Total Labour Cost |  |  | $30,000.00 |

### Other Direct Project Costs

| Item | Cost |
| --- | --- |
| Site mobilisation and transport / travel expenses | $3,000.00 |
| Heavy plant and equipment hire (excavator, roller, paver) | $10,000.00 |
| NATA Soil hydrology, permeability and water quality testing | $3,000.00 |
| Environmental overheads and miscellaneous site expenses | $5,000.00 |
| Total Other Costs | $21,000.00 |

### Total Project Budget Summary

| Cost Category | Total Cost |
| --- | --- |
| Materials total | $150,542.60 |
| Labour total | $30,000.00 |
| Mobilisation / travel | $3,000.00 |
| Plant and equipment hire | $10,000.00 |
| Quality and inspection testing | $3,000.00 |
| Miscellaneous site expenses | $5,000.00 |
| Total Direct Baseline Budget | $204,542.60 |
| Contingency allowance | 10% ($20,454.26) |

Section D: Procurement Delivery Staging and Schedules

To support pavement laying sequences without site congestion, materials will be delivered under the following schedule:

- Month 1: 40% of structural pavement materials delivered to site.

- Months 2–3: 30% of materials delivered.

- Months 4–6: Final 30% of materials delivered.

Section E: Milestone Review Intervals

Project income, expenditure and earned value performance will be audited at the following set intervals:

| Milestone | Timing | Engineering Deliverables | Procurement Delivery Schedule | Project Control and Audit |
| --- | --- | --- | --- | --- |
| Milestone 1 | Month 1 | • Site establishment, traffic management, and environmental controls. • Initial bulk earthworks, geometric cut-and-fill realignment. • Subgrade stabilisation and existing pavement milling/stripping. | Initial Allocation Delivery of primary structural pavement materials (sub-base aggregate, stabilisation agents, geotextiles). | Baseline Audit: Initial EVM baseline review (PV vs. EV vs. AC), early pavement materials stock verification, and sign-off on earthworks/subgrade readiness. |
| Milestone 2 | Month 2-3 | • Mainline pavement rehabilitation (base layer placement and compaction). • Structural upgrades to culverts, drainage crossings, and road embankments. • Heavy-vehicle shoulder widening and sub-surface drainage installation. | Progress Allocation Delivery of intermediate structural and rehabilitation materials (bituminous binders, asphalt mixes, structural concrete/drainage units). | Mid-Term Review: Full SPI and CPI performance audit, material density/compaction compliance checks, and forecast-to-complete cost reconciliation. |
| Milestone 3 | Month 4-6 | • Final wearing course application and high-capacity surface sealing. • Safety integration: guardrails, heavy vehicle line marking, and signage. • Defect rectification, site demobilisation, and asset handover to authority. | Final Allocation Final delivery of surface wearing course materials, line-marking supplies, and finishing hardware. | Final Closeout: Final contract closeout audit, Earned Value reconciliation, variation assessment, release of retention, and formal authority asset handover. |

Section F: Supplier Evaluation and Selection Process

Offers from quarry operators, asphalt suppliers, and material vendors will be evaluated using the following criteria:

### Offer Evaluation

- Delivery Capability: Guaranteed delivery lead times matching site paving rates.

- Quality and Compliance: Material compliance with road authority technical specifications.

- Responsiveness: Commercial capability and agility to adjust supply rates for weather delays.

- Commercial Value: Competitive unit rates and transparent haulage fees.

### Operational Capacity Analysis

- Verification of supplier quarry/plant physical capacity to supply required daily volume.

- Assessment of logistics and dispatch scheduling systems to prevent site haulage bottlenecks.

Section G: Organisational Financial Policies and Governance

All project expenditure and reporting must adhere strictly to Velocity Civil corporate governance protocols:

- Budgeting Methodology: Bottom-up cost estimation must be used to establish baseline budgets.

- Accounting Standards: All financial assets, project liabilities and progress claims must be recorded using double-entry bookkeeping.

- Document Retention: All delivery dockets, test certificates, contracts and financial records must be retained and stored according to Velocity Civil’s policies and procedures.

- Variance Reporting (0%--5%): Variations within 0% to 5% of budget must be formally reported with a written root-cause explanation before entering into project financial records.

- Major Variation Process (>5%): Any expenditure or scope change exceeding a 5% cost variation requires a formal Change Request submitted to the Project Manager for approval.