## Lessons Learned Register

Purpose: This register captures structural, operational, and design insights to prevent recurrence of design gaps, close the feedback loop between drafting and construction, and inform vocational training modules.

| ID | Project / Phase | Category | Description of Issue / Event | Lessons Learned and Root Cause Analysis | Corrective Actions and KMS Update |
| --- | --- | --- | --- | --- | --- |
| 001 | Blackwood Highway Detailed Design | Technical (Design) | 3D modelling elements failed to account for accurate pavement cross-fall interfaces, resulting in local stormwater ponding on a flat super-elevation transition. | Standard 2D sections hid geometric complexities at the transition zone. Root Cause: Lack of dynamic multi-string correlation within the drainage design software. | Mandated string-to-string surface verification checks in all highway designs. Updated the Civil Cadets Training Manual (Unit: Civil Design). |
| 002 | Orchard Industrial Park Precast Structural | Risk and Structural | Torsional stress cracking occurred during lifting operations on custom eccentric precast retaining units due to unaligned centre-of-mass calculations. | Dynamic lifting forces were analysed strictly on static loading principles. Root cause: Rigging geometry variations were omitted from the final structural engineer's check. | Rigging configuration models must match exact engineering mechanics parameters. Incorporated case study into the Precast Construction Engineering Guideline. |
| 003 | Riverina Subdivisions Geotechnical Site | Process / Surveys | Mass balance earthworks modelling underestimated actual cut volume by 15%, causing structural material shortfalls and unexpected off-site disposal fees. | Topographical survey data utilised interpolation spacing that was too sparse over highly irregular terrain contours. | Mandated maximum drone survey grid density bounds for variable terrains. Updated the IMS Subcontractor Pre-flight Checklist |
| 004 | Emu Creek Bridge Outfall Hydrology NCC | Compliance | Scour protection dimensions failed to pass environmental authority certification criteria due to outdated rainfall intensity-frequency duration parameters | Design inputs relied on old local council data matrices instead of updated national engineering guidelines. | Created a mandatory Design Basis Review Form in the IMS requiring verification of active climate data against current regulatory standards before drafting. |
| 005 | Apex Commercial Hub Utility Interface | Coordination | High-voltage conduit configurations clashed with primary structural pad footings during early excavation works, stopping site execution for 4 days. | Subcontractor utility layouts were updated using isolated 2D sketches without full cross disciplinary compilation in the federated BIM environment. | Instituted automatic clash detection cycles under the supervision of the Digital Engineering and BIM Manager prior to issuing packages for construction. |
| 006 | Somerset Bulk Earthworks Drafting Standards | Technical (CAD) | Field execution layouts were compromised because multi-layered structural drawing files displayed incorrect dynamic scale viewports upon print extraction | CAD trainees used multi-scale text annotations across legacy layer variations without locking the presentation viewports. | CAD trainees used multi-scale text annotations across legacy layer variations without locking the presentation viewports. |