Project Brief – Riverbend Residential Subdivision

| Activity Riverbend Residential Subdivision | Location O'Connell Estate Greenfield Residential Development Lot 102, O'Connell Road, Wisemans Creek VIC 3853 |
| --- | --- |

## Section A: Project Brief

## Velocity Civil has been engaged to deliver the civil infrastructure for a 45-lot greenfield residential development in Wisemans Creek. A high-priority focus of this stage is the structural modelling, bulk excavation and technical installation of a dual-basin Water Sensitive Urban Design (WSUD) stormwater management system. This critical infrastructure is designed to control peak flow rates and treat urban runoff prior to discharge into the adjacent river ecosystem.

## Section B: Project Overview

### Project Deliverables

### Structural modelling, bulk basin formation and installation across 3,000 m2 of dual-basin WSUD bioretention treatment surface (including sub-surface drainage lines, edge restraints, structural inlet/outlet transitions and associated civil earthworks).

### Project Objectives

### Timeline: Complete all WSUD basin structural and civil works within the client’s strict 6-month schedule.

### Quality and Specifications: Fully comply with regional council engineering guidelines, state WSUD technical design specifications and environmental river protection standards.

### Financial Performance: Procure all specialised filter media, piping, plant and labour within the defined budget to achieve target project margin.

### Project Duration

Six (6) months.

### Contract Value

- Total contract price: $400,000

- Cost objectives:

  - Keep direct project costs below $220,000.

  - Eliminate waste, rework, and unapproved plant demurrage.

## Section C: Procurement Requirements and Cost Breakdown

### The construction contract establishes a baseline material unit cost of $50.00 per metre square for specialised WSUD bioretention filter layers and drainage media installation.

### Material Procurement Requirements and Unit Costs

| Material Item | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- |
| WSUD Bioretention filter media and gravel layer | 3,000 m2 | $50.00 / m2 | $150,000.00 |
| Perforated sub-surface underdrain pipe (300 m) | 300 m | $1.57 / m | $471.00 |
| Basin edge restraint / impermeable liner (20 m) | 20 m | $1.97 / m | $39.40 |
| Scour protection / inlet transition spillway (20 m) | 20 m | $1.61 / m | $32.20 |
| Total Material Cost |  |  | $150,542.60 |

### Labour / Human Resource Requirements

| Role | Total Hours | Hourly Rate | Total Cost |
| --- | --- | --- | --- |
| 1Project Civil Engineer / Project Manager and Project Procurement Manager | 150 hrs | $60.00 / hr | $9,000.00 |
| 3 Experienced Civil Operators / Plant Crew | 600 hrs | $40.00 / hr | $21,000.00 |
| Total Labour Cost |  |  | $30,000.00 |

### Other Direct Project Costs

| Item | Cost |
| --- | --- |
| Site mobilisation and transport / travel expenses | $3,000.00 |
| Heavy plant and equipment hire (excavator, roller, paver) | $10,000.00 |
| NATA Soil hydrology, permeability and water quality testing | $3,000.00 |
| Environmental overheads and miscellaneous site expenses | $5,000.00 |
| Total Other Costs | $21,000.00 |

### Total Project Budget Summary

| Cost Category | Total Cost |
| --- | --- |
| Materials total | $150,542.60 |
| Labour total | $30,000.00 |
| Mobilisation / travel | $3,000.00 |
| Plant and equipment hire | $10,000.00 |
| Quality and inspection testing | $3,000.00 |
| Miscellaneous site expenses | $5,000.00 |
| Total Direct Baseline Budget | $204,542.60 |
| Contingency Allowance | 10% ($20,454.26) |

Section D: Procurement Delivery Staging and Schedules

To enable the seamless sequence of civil earthworks, sub-surface drainage lines, and dual-basin WSUD surface treatment while preventing site congestion, material deliveries are scheduled as follows:

- Month 1: 40% of primary drainage piping, basin liners and bulk filter media delivered to site.

- Months 2–3: 30% of specialised media and structural transition components delivered.

- Months 4–6: Final 30% of materials delivered for final basin commission and river outfall tie-ins.

Section E: Milestone Review Intervals

Project income, expenditure and earned value performance will be audited at the following set intervals:

| Milestone | Timing | Key Civil Focus | Procurement | Financial Audit Gate |
| --- | --- | --- | --- | --- |
| Milestone 1 | Month 1 | Bulk earthworks, basin excavation, trunk piping | 40% (Piping, liners, bulk media) | Baseline EVM & initial earthworks claim |
| Milestone 2 | Month 2-3 | Basin liner/media installation, structural GPTs/inlets | +30% (Specialised media & transition components) | Mid-project SPI/CPI audit & media permeability test |
| Milestone 3 | Mon th 4-6 | River outfall tie-in, basin commissioning, lot prep | +30% (Outfall structures, vegetation & commissioning stock) | Final contract closeout, variation audit & environmental sign-off |

Section F: Supplier Evaluation and Selection Process

### Offers from quarry operators, asphalt contractors, precast vendors and civil material suppliers will be evaluated using the following criteria.

### Offer Evaluation

### Delivery Capability: Guaranteed delivery rates matching civil excavation and lining schedules.

### Quality and Compliance: Certified hydraulic conductivity and hydraulic performance testing for filter media meeting WSUD design parameters.

### Responsiveness: Agility to modify material delivery schedules around rainfall events and site wet-weather protocols.

### Competitive Value: Cost-effective material pricing, transparent haulage fees and batch consistency.

### Operational Capacity Analysis

### Verification of supplier production volume and certified media stockpiles.

### Assessment of haulage fleet availability to maintain steady deliveries to the Wisemans Creek development site.

Section G: Organisational Financial Policies and Governance

All expenditure, progress claims and subcontractor engagements on the subdivision must adhere strictly to Velocity Civil corporate governance protocols:

- Budgeting Methodology: Bottom-up cost estimation must be used to establish baseline package budgets.

- Accounting Standards: All project financial assets, liabilities and progress claims must be recorded in accordance with double-entry bookkeeping principles.

- Record Keeping: All delivery dockets, batch test certificates, NATA soil conductivity lab results, contracts and invoices must be retained and stored according to Velocity Civil’s policies and procedures.

- Variance Reporting (0%--5%): Cost variations between 0% and 5% must be formally reported to the Project Manager with a written root-cause explanation before entry into financial ledgers.

- Major Variation Threshold (>5%): Any scope or material price variation exceeding 5% requires a formal Change Request submitted to the Project Manager prior to committing funds.