Tender Submission – Oakhaven Regional Council

| Activity | 1.2km Rural Collector Road Widening and Safety Upgrade |
| --- | --- |
| Location | Oakhaven-Oberon Road Corridor (Chainage 12+400 to 13+600) |
| Company Name | TerraForge Civil |
| ABN / CAN | 31 654 987 321 / ACN: 654 987 321 |
| Business Address | Unit 4, 112 Enterprise Drive, Bathurst NSW 2795 |
| Primary Contact | Graham Tweed (Senior Estimator) |
| Contact Information | g.tweed@terraforge.com.au ¦ (02) 6331 9400 |
| Classification | Mid-Tier Civil Design and Construction |

## Section A: Scope Overview

## Provision of end-to-end geotechnical site investigation, laboratory testing, feature level survey, and final engineering report to support detailed pavement design and earthworks execution.

## Section B: Proposed Scope of Works and Methodology

| Stages | Methodology |
| --- | --- |
| Phase 1 Aerial and Ground Spatial Capture | High-resolution UAV Drone LiDAR and Photogrammetry Ground Control Point (GCP) network setup (AHD/GDA2020) 3D Point Cloud generation and Digital Terrain Model (DTM) extraction |
| Phase 2 Geophysical and Subsurface Testing | Non-destructive Seismic Refraction Profiling along the 1.2 km corridor Targeted Cone Penetration Testing (CPT) at 8 locations Standard Slotted Piezometer installation at 2 locations |
| Phase 3 Laboratory and Pavement Analysis | Accelerated NATA-certified testing suite Dynamic shear rheometer and fhydrometer analysis Environmental contaminant screening (EPA Suite) |
| Phase 4 Integrated Deliverables | Final Geotechnical and Survey Report (RPEQ/CPEng signed) 3D BIM-compatible Civil 3D Model and LAS Point Clouds Pavement life-cycle assessment and subgrade report |

## Section C: Key Project Personnel

| Role | Key Qualifications | Responsibilities |
| --- | --- | --- |
| Project Director | B. Eng (Civil), MIEAust, RPEQ / Registered Professional Engineer | Executive oversight, contract compliance, quality management and principal client liaison. |
| Lead Survey and Spatial Specialist | B. Surveying, Certified UAV Drone Operator (CASA RePL) | Overseeing UAV LiDAR flights, ground control point (GCP) network setup and 3D point cloud generation. |
| Senior Geotechnical Engineer | Ph.D. Geotechnical Engineering, B. Eng (Civil) | Supervising CPT testing, seismic refraction analysis, piezometer data interpretation and certifying the final report. |
| Environmental and Safety Officer | B. Env.Sc, Cert IV Work Health and Safety (WHS) | Managing environmental contaminant screening (EPA suite), traffic safety management and site-specific SWMS. |

## Section D: Health, Safety and Environmental Quality Assurance

| Work Health and Safety (WHS) | - Non-destructive hydro-vacuum excavation required for all subsurface investigations. - Dynamic risk assessment and site-specific Safe Work Method Statements (SWMS) prior to CPT rig deployment. - Remote UAV/LiDAR mapping used to reduce physical personnel exposure on active road shoulders. |
| --- | --- |
| Traffic Management | - Low-impact mobile traffic control setups to maintain continuous two-way regional traffic flow. - Mandatory high-visibility vehicle mounted advance warning boards and certified traffic control personnel. |
| Environmental Protection | - Real-time turbidity monitoring and spill kits on-site during deep piezometer drilling. - Continuous EPA-certified contaminant screening for spoil and soil waste classification. - Flight path optimization for UAV operations to prevent disruption to local wildlife and livestock. |
| Quality Assurance (QA | - All soil and rock testing conducted exclusively through NATA-accredited laboratories. - Calibration and survey verification of UAV LiDAR data against established ground control points (GCPs). - Dual-sign-off engineering validation process by RPEQ/CPEng qualified engineers prior to report release. |

### Section E: Commercial Scheduling and Pricing

Fixed Fee Pricing Schedule

| Item | Description | Qty | Unit | Unit Rate (AUD) | Total Cost (excl. GST) |
| --- | --- | --- | --- | --- | --- |
| 1.0 | UAV LiDAR Flight and Ground Control Survey | 1.2 | Km | $2,800 | $3,360 |
| 2.0 | Non-Destructive Geophysical Profiling (Seismic) | 1.2 | Km | $4,000 | $4,800 |
| 3.0 | Cone Penetration Testing (CPT) Rig Operation | 8 | Rig Days | $1,200 | $9,600 |
| 4.0 | Subsurface Piezometer and Environmental Sampling | 2 | Location | $2,100 | $4,200 |
| 5.0 | Comprehensive NATA Soil Mechanics Testing | 1 | Lump | $8,500 | $8,500 |
| 6.0 | 3D BIM Modeling and Final Engineering Report | 1 | Item | $9,000 | $9,000 |
| Total |  |  |  |  | $39,460 |

### Section D: Proposed Project Schedule and Key Milestones

Target Completion Window: 4 Weeks from Notice to Proceed (NTP).

| Schedule | Milestones |
| --- | --- |
| Week 1 | GCP Survey complete and initial LiDAR Point Cloud Captured |
| Week 2 | Field investigation phase complete and site demobilisation |
| Week 3 | Laboratory Test Certificates issued and DTM finalised |
| Week 4 | Delivery of Final Geotechnical and Survey Report Package |