Tender Submission – Oakhaven Regional Council

| Activity | 1.2km Rural Collector Road Widening and Safety Upgrade |
| --- | --- |
| Location | Oakhaven-Oberon Road Corridor (Chainage 12+400 to 13+600) |
| Company Name | Redstone Civil Engineering |
| ABN / CAN | 84 912 345 678 / 912 345 678 |
| Business Address | Level 2, 45 Industrial Parkway, Orange NSW 2800 |
| Primary Contact | James Radford (Senior Estimator / Contracts Lead) |
| Contact Information | j.radford@redstone.com.au ¦ (02) 6330 1800 |
| Classification | Mid-Tier Civil Design and Construction |

## Section A: Scope Overview

## Provision of end-to-end geotechnical site investigation, laboratory testing, feature level survey and final engineering report to support detailed pavement design and earthworks execution.

## Section B: Proposed Scope of Works and Methodology

| Stages | Methodology |
| --- | --- |
| Stage 1 Site Setup and Preliminary Survey | Dial Before You Dig (DBYD) / utility location High-accuracy feature and level survey (1.2 km corridor) Establish control points (RTK GPS and total station) |
| Stage 2 Geotechnical Field Investigation | Continuous flight auger / boreholes (6x to 3m–5m depth) Dynamic Cone Penetrometer (DCP) testing @ 100m intervals Environmental soil sampling (waste classification) |
| Stage 3 Laboratory Analysis.) | California Bearing Ratio (CBR) testing (soaked/4-day) Particle Size Distribution (PSD) and Atterberg Limits Moisture Condition Value (MCV) and Compaction Testing |
| Stage 4 Reporting and Deliverables | Comprehensive Geotechnical Investigation Report CivilCAD / AutoCAD 3D TIN Surface and Feature Maps Subgrade assessment and pavement thickness options |

## Section C: Key Project Personnel

| Role | Name / Title | Key Qualifications | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | Lead Civil Engineer (RPEQ / CPEng) | 12+ yrs Civil Infrastructure | Overall delivery, client liaison, quality control |
| Senior Geotechnical Engineer | Principal Geologist / Engineer | B. Eng (Civil/Geotech), MIEAust | Drilling supervision, lab oversight, report certification |
| Senior Civil Surveyor | Registered Land Surveyor | B. Surveying | Corridor survey, DTM generation, boundary verification |

## Section D: Health, Safety and Environmental Quality Assurance

| Traffic Management | Implementation of low-impact mobile lane closures in compliance with state road authority guidelines. |
| --- | --- |
| Safety and Permits | JSAs / SWMS generated prior to ground break; non-destructive hydro-excavation used for all utility verification boreholes. |
| Quality Standard | Certified to ISO 9001 (Quality Management System) and NATA-accredited laboratory testing partners. |

### Section E: Commercial Scheduling and Pricing

Fixed Fee Pricing Schedule

| Item | Description | Qty | Unit | Unit Rate (AUD) | Total Cost (excl. GST) |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Project setup and utility clearance | 1 | Item | $3,200 | $3,200 |
| 2.0 | Feature and contour survey (1.2 km Corridor) | 1.2 | Km | $4,500 | $5,400 |
| 3.0 | Borehole drilling and in-situ testing (6 Holes) | 6 | Each | $1,850 | $11,100 |
| 4.0 | Dynamic Cone Penetrometer (DCP) field testing | 12 | Test | $250 | $3,000 |
| 5.0 | NATA laboratory testing suite (CBR, PSD, Limits) | 1 | Lump | $6,800 | $6,800 |
| 6.0 | Geotechnical Investigation and Site Survey Final Repo | 1 | Item | $7,500 | $7,500 |
| Total |  |  |  |  | $37,000 |

### Section D: Proposed Project Schedule and Key Milestones

Target Completion Window: 4 Weeks from Notice to Proceed (NTP).

| Schedule | Milestones |
| --- | --- |
| Week 1 | DBYD clearance, site setup, traffic management plan approval, and control point survey. |
| Week 2 | On-site drilling, DCP testing, soil sampling, and feature level survey completion. |
| Week 3 | NATA laboratory testing and data processing. |
| Week 4 | Final engineering report delivery, AutoCAD survey models (.DWG), and client debrief. |