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Tender Submission – Oakhaven Regional Council

	Activity
	1.2km Rural Collector Road Widening and Safety Upgrade

	Location
	Oakhaven-Oberon Road Corridor (Chainage 12+400 to 13+600)

	Company Name
	Redstone Civil Engineering

	ABN / CAN
	84 912 345 678 / 912 345 678

	Business Address
	Level 2, 45 Industrial Parkway, Orange NSW 2800

	Primary Contact
	James Radford (Senior Estimator / Contracts Lead)

	Contact Information
	j.radford@redstone.com.au | (02) 6330 1800

	Classification
	Mid-Tier Civil Design and Construction 



Section A: Scope Overview

Provision of end-to-end geotechnical site investigation, laboratory testing, feature level survey and final engineering report to support detailed pavement design and earthworks execution.

Section B: Proposed Scope of Works and Methodology

	Stages
	Methodology

	Stage 1
Site Setup and Preliminary Survey
	Dial Before You Dig (DBYD) / utility location
High-accuracy feature and level survey (1.2 km corridor)
Establish control points (RTK GPS and total station)

	Stage 2
Geotechnical Field Investigation
	Continuous flight auger / boreholes (6x to 3m–5m depth)
Dynamic Cone Penetrometer (DCP) testing @ 100m intervals
Environmental soil sampling (waste classification)

	Stage 3
Laboratory Analysis.)
	California Bearing Ratio (CBR) testing (soaked/4-day)
Particle Size Distribution (PSD) and Atterberg Limits
Moisture Condition Value (MCV) and Compaction Testing

	Stage 4
Reporting and Deliverables
	Comprehensive Geotechnical Investigation Report
CivilCAD / AutoCAD 3D TIN Surface and Feature Maps
Subgrade assessment and pavement thickness options



Section C: Key Project Personnel

	Role
	Name / Title
	Key Qualifications
	Responsibilities

	Project Manager
	Lead Civil Engineer (RPEQ / CPEng)
	12+ yrs Civil Infrastructure
	Overall delivery, client liaison, quality control

	Senior Geotechnical Engineer
	Principal Geologist / Engineer
	B. Eng (Civil/Geotech), MIEAust
	Drilling supervision, lab oversight, report certification

	Senior Civil Surveyor
	Registered Land Surveyor
	B. Surveying
	Corridor survey, DTM generation, boundary verification



Section D: Health, Safety and Environmental Quality Assurance

	Traffic Management
	Implementation of low-impact mobile lane closures in compliance with state road authority guidelines.

	Safety and Permits
	JSAs / SWMS generated prior to ground break; non-destructive hydro-excavation used for all utility verification boreholes.

	Quality Standard
	Certified to ISO 9001 (Quality Management System) and NATA-accredited laboratory testing partners.



Section E: Commercial Scheduling and Pricing
Fixed Fee Pricing Schedule
	Item
	Description
	Qty
	Unit
	Unit Rate (AUD)
	Total Cost (excl. GST)

	1.0
	Project setup and utility clearance
	1
	Item
	$3,200
	$3,200

	2.0
	Feature and contour survey (1.2 km Corridor)
	1.2
	Km
	$4,500
	$5,400

	3.0
	Borehole drilling and in-situ testing (6 Holes)
	6
	Each
	$1,850
	$11,100

	4.0
	Dynamic Cone Penetrometer (DCP) field testing
	12
	Test
	$250
	$3,000

	5.0
	NATA laboratory testing suite (CBR, PSD, Limits)
	1
	Lump
	$6,800
	$6,800

	6.0
	Geotechnical Investigation and Site Survey Final Repo
	1
	Item
	$7,500
	$7,500

	Total
	$37,000



Section D: Proposed Project Schedule and Key Milestones
Target Completion Window: 4 Weeks from Notice to Proceed (NTP).
	Schedule
	Milestones

	Week 1
	DBYD clearance, site setup, traffic management plan approval, and control point survey.

	Week 2
	On-site drilling, DCP testing, soil sampling, and feature level survey completion.

	Week 3
	NATA laboratory testing and data processing.

	Week 4
	Final engineering report delivery, AutoCAD survey models (.DWG), and client debrief.
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Company Name  Redstone Civil Engineering  

ABN / CAN  84 912 345 678 / 912 345 678  

Business   Address  Level 2, 45 Industrial Parkway, Orange NSW 2800  

Primary Contact  James Radford (Senior Estimator / Contracts Lead)  

Contact Information  j.radford@ redstone .com.au | (02) 6330 1800  
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